## Slide 1
Overview & tutorial with screen shots
NEW VERSION OCT 21, 2012
Notes: This PowerPoint provides a short introduction to Miradi – a new software program for managing conservation projects <click>
It covers general overview and navigation features including entering basic project information <click>
It covers how to create a situation analysis diagram to help guide the selection of strategies <click>
And building results chains to explicitly show the results you are trying to achieve by implementing certain strategies
It covers how to add Objectives, Indicators, Monitoring Methods, as well as additional detail on the Activities being implemented<click>
Once the data is entered, you can view or edit within the Planning View <click>
You can generate a number of standard reports and export data from Miradi <click>

## Slide 2: Miradi tutorial with screen shots
Basic Navigation, Summary View, data entry slides 3-6
Situation Analysis  Result Chain example
Objective data entry
Indicator/Measurement data entry
Activity data entry
Strategic Plan View – Standard
Strategic Plan View – Custom
Work Plan View – Layout
Work Plan – Project Settings
Work Plan – Work Unit Data Entry
Work Plan – Expense Data Entry
Reports & Exporting data
 
 
 
 
 
 
 
Proceed to next slide to walk through this sequence or click on the mouse icons to jump to a particular topic (in Slide Show Mode). Each topic includes a button to come back here.
Basic Features
Target Viability - Simple approach
Target Viability - KEA approach
Threat Ranking – Simple mode
Threats Ranking – Stress-based mode
Viability & Threats
 
 
 
 
 
 
 
 
 
View in Slide Show Mode

## Slide 3
3. Opening an existing file
1. Creating a new project
2. Importing a file
Start by:
Click this button in any screen to return to directory

Intro - 1 of 4
Notes: Miradi is available free of charge to all TNC staff and to partners we are working with on joint projects – the final slide of this presentation includes a download link for TNC staff
Once you download and install Miradi, you can do one of 3 things:<click>
Create a new project <click>
Import a Miradi zipped file that someone sent to you<click>
Open an existing project file from the list

## Slide 4
Access More Info, Examples, Workshop Tips
Summary view (pull-down menu to switch to other views)
Instructions walk you through data entry, step-by-step
Move splitter to adjust size of upper/lower panels
Tabs with fields for entering basic project information, team, location, etc.

Intro - 2 of 4
Notes: Miradi has 6 main views, which you access via this pull-down menu in the upper left of the screen <click> -- It will open to the Summary view, where you enter basic project information like name, description, team members<click>
The upper portion of the screen includes an set of instructions for entering information for that view, you can scroll forward and backward through each step by clicking Next or Previous buttons <click>
There are a number of tabs for entering different types of information like other organizations involved, project scope, location, <click>
The buttons in the upper right take you to more information, bring up examples, or provide hints for carrying out steps in a workshop setting <click>
You can easily adjust this splitter to change the screen area devoted to the instructions versus the data entry section

## Slide 5
Organization-specific tab & fields for Miradi sponsors
Buttons for standard pick lists – TNC Operating Unit and Terrestrial, Marine, & Freshwater Ecoregions

Intro - 3 of 4
Notes: On the TNC tab, you can get Miradi help via email and enter or view TNC-specific information (some to be transferred from ConPro) <click>
There are standard pick lists for TNC Operating Units and Terrestrial, Marine, and Freshwater ecoregions

## Slide 6
Diagram View is the main data entry view in Miradi
Click on a factor before adding a new one to automatically link the 2 factors
Click on buttons to add factors, check boxes to turn layers on or off
Splitter can move bar left/right
Tabs for Conceptual Model Diagrams & Results Chains – right click to create new diagrams or to rename existing diagrams
Zoom settings, including “Zoom to fit”
Miradi automatically saves – use “undo” to discard changes

Right-mouse click to pull up menu for many functions, including creating & deleting bend points and creating Group Boxes
Double-click on factors to open properties & add objectives, indicators & more
Intro - 4 of 4
Notes: The Diagram View is the main data entry view for Miradi <click>
You can insert different types of objects into the diagram by clicking on the buttons in the control bar <click>
There are 2 tabs, one for Conceptual Models (situation analysis diagrams) and another for Results chains, and you can have as many separate diagrams on each tab and easily copy or move information between the diagrams <click>
When you highlight a factor BEFORE clicking on another factor, it will automatically establish a link between the two for you. Otherwise, hold the shift key while clicking on 2 factors then click on the “Insert Link” button <click>
The right-mouse button will bring up a powerful set of options including creating and deleting bend points, modifying Group Boxes, entering a Brainstorm mode <click>
You can double-click on factors to enter information on objectives, indicators, and other information (you’ll see this shortly) <click>
You can create more space for your diagram area by adjusting this splitter <click>
There are zoom tools to zoom in and out, including a Zoom-to-Fit button that will scale the diagram to fill the diagram area <click>
Miradi automatically saves as you work, you can use a very robust undo feature to discard changes (you can go WAY back)

## Slide 7
Direct Threats
Contributing Factors
& Strategies
Target

Conceptual Model
Results Chain
Highlight strategy then right-click & select to build a draft Results Chain for a specific chain from your Conceptual Model (or alternatively, build a Result Chain from scratch, directly from Control Bar menu)
Notes: This shows the building of a situation analysis for a couple of the threats to coral reefs <click>
These are some of the direct threats <click>
And the contributing factors behind the direct threats, as well as opportunities (like the Indonesian Government’s Coral Triangle Challenge) <click>
Add the addition of strategies, directed in this case towards some of the contributing factors <click>
Miradi allows you to convert a situation analysis diagram into a results chain by highlighting one or more strategies and right-clicking and selecting the Create Results Chain option – <click>
You can then re-word the factors to convey desired results, as you can see here.
You can also enter Results Chains directly, in the same way you create situation analysis diagrams

## Slide 8
Add Measurable Objectives to the Results Chain(s)
See next slide for the Dialog Box for that comes up when you Double-click on this factor to enter or edit Objectives

Notes: You can add details such as objectives, indicators and other information to any of the factors in the diagram, by double-clicking on the factors
The Intermediate Results provide a short summary of desired changes but it’s a good idea to have more detailed objective statements associated with many of the factors in the diagram <click>
Here you can see that specific goals have been added for the target and 5 objectives where added to other factors in the diagram <click>
The next slide will show you the objectives associated with the “Increase in MPAs” intermediate result

## Slide 9
User assigned ID code
Short name
Full Objective name
Shows details for the highlighted row
1 Objective entered
Adding/Editing Objectives for an Intermediate Result
Adjust default Miradi associations between Objectives and Indicators or Strategies/Activities

Gray cells show relationships established in the diagram
Notes: You can add and delete objectives or make exact copies (clones) of existing objectives (something you might do to save data entry time if you have a similar objective already entered)
Here you can see 2 objectives have entered <click>
The lower panel shows details for whatever row is highlighted in the upper table
If you’d like the user can assign ID codes to any objective <click>
The name field is intended to capture a short version of the objective <click>
Whereas the Text field provides a place to write a full, SMART objective statement <click>
The cells with gray backgrounds show you relationships established within the diagram <click>
You can adjust the default association between objectives and indicators or objectives and strategies by clicking on these buttons

## Slide 10
Add Indicators & Indicator Measurement information
See next slide for the Dialog Box that comes up when you Double-click on the Indicator icon for this factor to enter or edit Indicators & Measurements

Notes: For every factor that has an objective, you should also add indicators that will be tracked to measure progress towards achieving the objectives <click>
Here you can see that a variety of indicators have been added to the results chain <click>
The next slide will bring up the indicator properties associated with this intermediate result

## Slide 11
Indicator & measurements over time (actual measures information)
Shows details for the highlighted row
Most recent indicator measurement information
Past measurement information
Desired future result value & date
Indicator for Objective

Trend (Flat – no major changes)
Indicates data from quantitative sources
Notes: We are now looking at the indicators tab.
The buttons allow you to create or delete indicators or measurement values (or make exact copies of an existing indicator) <click>
The triangle denotes the indicator – here the ha’s of MPAs that have been designated <click>
Older indicator measurement information is reported here <click>
The most recent measurement information from Sept 07 is reported here <click>
If you want, you can also enter the desired future status (information from the objective) to clearly show the difference between indicator measurements and the results you are trying to achieve
The lower panel shows details for the highlighted row where you can assign dates using a little calendar widget, enter the indicator value, and provide any details that you want (here, it shows the size of each of the individual designated MPAs).
You can specify a trend assignment using a drop-down menu (here assigned as a “Strong Increase” based on the big jump since the last measurement, in fact exceeding the June 2008 desired result)
There is also a pull-down for the data source – labeled “Intensive Assessment” here because this indicator is calculated via GIS analyses

## Slide 12
Add Activities & high-level work plan information for Strategies
See next slide for the Dialog Box that comes up when you Double-click on this factor to enter or edit Activities
Results Chain Diagram

Notes: You can also add more details at the level below the Strategies – entering Activities and who, when, and cost information <click>
The next slide will show you the properties associated with this Strategy hexagon

## Slide 13
Shows details for the highlighted row
Activities tab on the Strategies Dialog Box
Activity data entry
Name of Strategy
2 Activities Entered

Notes: You can see the name of the Strategy at the top <click>
We’re looking at the Activities tab (you can see there are also Objectives and Indicators tabs) <click>
There are 4 Activities entered for this strategy <click>
The lower panel shows details for the highlighted Activity – you can specify cost information, <click>
or who is responsible for implementing this activity

## Slide 14
Strategic Plan View – standard view displays
Standard Planning Views (Action Plan selected)
Toggle control for Objective – Strategy relationship
Expand or collapse all rows
Click “-” or “+” to collapse/expand tree
Details for the selected row are displayed in the lower panel where they can be edited
Custom View (see next slide)
Side tabs to access additional fields


## Slide 15
Strategic Plan View – Custom view display
Check boxes for the columns you want in the table
Can start with current or blank view
Assign name to the custom view
Check boxes for the rows you want in the table
Any table can be exported to Word – use RTF File option
Custom View


## Slide 16

Work Plan View - Layout
Work Plan table
Enter people
Enter Account Codes
Enter Budget Centers
Optional Category 1
Optional Category 2
Create pivot table like summaries
Progress Ratings
Staff assignments
Work days
Expenses
Totals
Details for the selected row are displayed in the lower panel where they can be edited
Side tabs to access additional fields
Create Activities or Tasks
When

## Slide 17

Select “Edit” – “Preferences”
Work Plan – Project Settings
Specify currency
Specify key financial information
Specify fiscal year
Specify Start and End dates using date widget
Additional Financial Settings

## Slide 18
“When” column automatically filled out – reflects 4 years
When work days entered at finer grain (blue text - editable) – Total shifts to a roll-up field (not editable)
Data entered for rest of years (Note changing “Total” & “When”)
If second person is added, work days entered in top panel are split evenly in bottom panel. Top panel work days still blue & editable as long as even split between people.
If asymmetrical work day entry is entered in lower panel, additional edits must be made here (top panel no longer blue text, not editable).
Can shift to finer level of actions via the “Create…” button
Click “+” to show more detailed dates
Clicking “+” will continue to show more detail
Click “-” to collapse dates
If work days are added at Activity level – Miradi honors this finer-grain data as the new, improved estimate, Strategy row now rolls up Activity data and is no longer editable.
100 days entered as total across 4 years (Note blue text – editable)
Double-click in “Who” to open pick-list of people (add people in Project Resources tab)
Initials appear in top panel, Assignment entry appears in bottom panel

Work Plan – Work Effort Data Entry
Watch in Slide Show Mode

## Slide 19

Work Plan – Expense Data Entry
Switched display to show Expense columns instead of work day columns
Assigned to account code
Assigned to Funding Source (could be budget center)
User-entered expense description
Expense assigned to 2012 (editable in top or bottom panel – blue text)
Because 2011 expense is not editable – indicates finer scale expense exists – click “+” to expand
Click “-” to collapse
Expenses entered (and editable) at Quarter-level

## Slide 20
Full Report
Reports & Exporting Data
Reports View
Reports for individual sections

Notes: The Reports View allows you go generate and save standard reports (for example, you can export a project plan and results in a pdf file to share with partners) <click>
From within any view in Miradi, you can export a small compressed Miradi file (has an .MPZ suffix) <click>
You can export a full report with all content or <click>
Generate reports for individual sections of Mirad <click>
Reports can be saved as PDF files, or Open Office documents, diagrams and tables can be saved as JPEG or PNG files (you can increase diagram image quality by first zooming in closer). You can also export tables as images or as as tab-delimited tables
We are working with Miradi and TIS programmers to get develop ConPro-Miradi data exchanges

## Slide 21
The remaining slides describe target viability and threat ranking views in Miradi

## Slide 22
Target name
Overall target viability status
Create an indicator
Viability Analysis Mode: Simple
Set desired future status
Shows details for the highlighted row
Simple Viability Mode – Indicator & Desired Status


## Slide 23
Simple Viability Mode – Indicator Measurements
Shows details for the highlighted row
Document how measurements were obtained
Assign Trend category
Most recent indicator measurement information

Past measurement information

## Slide 24
Key Attribute Viability Mode – Indicator & Desired Status
Target name
Create an indicator
Viability Analysis Mode: Key Attribute
Shows details for the highlighted row
Create a KEA
Document how ratings and measurements were obtained
Set desired future status
Add one or more indicator rating descriptions


## Slide 25
Key Attribute Viability Mode – Indicator Measurements
Shows details for the highlighted row
Document how measurements were obtained
Assign Trend category

Most recent indicator measurement information
Past measurement information

## Slide 26
Simple Threat Ranking - Severity, Scope, & Irreversibility assigned to Direct Threats (Sources of Stress)
Miradi supports 2 Threat Ranking Modes


## Slide 27
Simple Threat Ranking Mode
Wizard will walk you through threat ranking
Produces TNC style Threat Summary Table (uses TNC roll-up rules)
First enter targets and threats in Diagram

Assign Scope, Severity, and Irreversibility Ratings

## Slide 28
Stress-based Threat Ranking - traditional TNC threat ranking:
Stress  Severity/Scope
Source  Contribution /
Irreversibility
Option (1) - Threat View (after Direct Threats [Sources] are entered)
Option (2) - Enter Stresses & Ranks via Target Properties in Diagram View (can be entered before Direct Threat entry)
Miradi supports 2 Threat Ranking Modes
2 Options
for data
entry/editing


## Slide 29
Option (1) - Threat View (after Direct Threats [Sources] are entered)
Stress-based Threat Ranking Mode
Wizard provides instructions
Select cell in table
Click to enter/edit stresses & stress ranks

Assign Direct Threat (i.e., Source) Contribution & Irreversibility Ranks
Create/Delete Stresses
Assign Severity & Scope ranks

## Slide 30
Double-click on Target then click on Stresses Tab
Create/Delete Stresses
Assign Severity & Scope ranks
Assign Direct Threat (i.e., Source) Contribution & Irreversibility Ranks using Options (1) or (2) – see previous 2 slides

Stress-based Threat Ranking Mode
Option (2) - Enter Stresses & Ranks via Target Properties in Diagram View (can be entered before Direct Threat entry)