STRATEGY RANKING IN THE OPEN STANDARDS FOR THE PRACTICE OF CONSERVATION

1. Criteria for assessing strategies:

Potential Impact - If implemented, will the strategy lead to desired changes in the situation at your project site?

- Very High - The strategy is very likely to completely mitigate a threat or restore a target.

- High - The strategy is likely to help mitigate a threat or restore a target.

- Medium - The strategy could possibly help mitigate a threat or restore a target.

- Low - The strategy will probably not contribute to meaningful threat mitigation or target restoration.

Note that there are at least two dimensions being rolled up into this rating: probability of positive impact and magnitude of change. The users will have to integrate these into their rating.

Feasibility - Would your project team be able to implement the strategy within likely time, financial, staffing, ethical, and other constraints?

- Very High - The strategy is ethically, technically, AND financially feasible.

- High - The strategy is ethically and technically feasible, but may require some additional financial resources.

- Medium - The strategy is ethically feasible, but either technically OR financially difficult without substantial additional resources.

- Low -The strategy is not ethically, technically, OR financially feasible.

These ratings are then rolled-up to give an overall summary rating for the strategy. Note that if a draft strategy is assigned any "red" colored rating, then the summary rating will also be "red."

## Rollup

Here is a relatively simple roll-up of the overall “Strategy Priority.”  At higher levels, a project has to be both feasible AND have a high potential impact to score high.  But at lower levels, either low feasibility OR low impact gives an overall low priority.

|  |  | Potential Impact |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Very High | High | Medium | Low |
| Feasibility | Very High | Very High | High | Medium | Low |
|  | High | High | High | Medium | Low |
|  | Medium | Medium | Medium | Medium | Low |
|  | Low | Low | Low | Low | Low |

2. Criteria to assess strategy progress:

Scheduled for future implementation: the strategy hasn’t started yet

Major Issues: ongoing, but has considerable problems that need attention

Minor Issues: ongoing, but has minor problems that need attention

On-Track: ongoing, generally on track

Completed: Successfully accomplished

Abandonada: No longer relevant or useful

The criteria presented here is consistent with Miradi