# Wednesday Sessions:

# Goals, and Strategy Selection

# Results Chains, Objectives and Activities

### Learning Objectives:

- Become familiar with the second step of the Open Standards. After completion of this session and practice, participants should be able to apply the CMP Open Standards to a real project by producing the following parts of a strategic plan:

- well-defined goals for all your targets

- strategies identified for key intervention points of your conceptual model

- Become familiar with the results chain tool. After completion of this session and practice, participants should be able to demonstrate their ability to apply the CMP Standards to a real project by producing the following parts of a strategic plan:

- Results chains or other formal description of your core assumptions

- Become familiar with objectives and activities as essential components of a project plan. After completion of this session and practice, participants should be able to demonstrate their ability to apply the CMP Standards to a real project by producing the following parts of a strategic plan:

- well-designed objectives for all direct threat reduction results and other key results from their results chain

- one or more activities for each strategy to help achieve their conservation objectives

| Time | Summary | Materials/Handouts |
| --- | --- | --- |
| 45 min 8.30-9.15 | Lecture 7 A. Define goals – A formal statement detailing a desired impact of a project, such as the desired future status of a target. B. Develop clear goals that follow these criteria: 1. Linked to targets – Directly associated with one or more of your conservation targets 2. Impact oriented – Represents the desired future status of the target over the long term 3. Time limited – Achievable within a specific period of time, generally 10 or more years. 4. Measurable – Definable in relation to some standard scale (numbers, percentage, fractions, or all/nothing states). Specific – Clearly defined so that all people involved in the project have the same understanding of what the terms in the goal mean. C. Strategically select strategies – a group of actions with a common focus that work together to reduce threats, capitalize on opportunities, or restore natural systems by: Developing a range of potential strategies Strategically selecting those activities that you can feasibly undertake D. A good strategy should meet the following criteria: Linked: directly affects one or more critical factors. Focused: Outlines specific courses of action that need to be carried out. Feasible: Accomplishable in light of the project’s resources and constraints. Appropriate: Acceptable to and fitting within site-specific cultural, social, and biological norms | ppt Goals & strategies |
| 30 min 9.15-9.45 | Lecture 8 Detailed overview on how to construct results chains that: Clarify assumptions about how strategies will contribute to conservation targets Adhere to the following criteria: Results oriented – Boxes contain desired results and not activities, Causally linked – There are clear “if…then” connections between successive boxes, Demonstrate change – Each box describes how you hope the relevant factor will change (e.g., improve, increase, or decrease) Reasonably complete – There are sufficient boxes to construct logical connections but not so many that the chain becomes overly complex, Simple – There is only one result per box | ppt Results Chains |
| 165 min 9.45-12.30 | Project team work: Goals, Strategies & Results Chains Following the instruction sheet, begin to identify goals and strategies Following the instruction sheet, begin to develop results chains using newsprint and post-its. Document final results chain in Miradi | Instruction sheet for goals and strategies Instruction sheet for results chains Criteria cards Computer with Miradi software (1 per group) Background documents on project |
| 12.30-13.30 | Lunch |  |
| 60 min 13.30 – 14.30 | Continuation Project team work |  |
| 30 min 14.30-15.00 | Lecture 9: Objectives & activities A. Define an objective – A formal statement detailing a desired outcome of a project such as reducing a critical threat B. Overview of the how to write good objectives that meet the following criteria: Outcome oriented – Represents necessary changes in critical threat and opportunity factors that affect one or more project goals, Measurable – Definable in relation to some standard scale (numbers, percentages, fractions, or all/nothing states), Time limited – Achievable within a specific period of time, Specific – Clearly defined so that all people involved in the project have the same understanding of what the terms in the objective mean, Practical – Achievable and appropriate within the context of the project site. C. Define an activity – A specific action or set of tasks undertaken by a project staff and/or partners to reach one or more objectives. | ppt Objectives & actvities |
| 180 min 15.00-18.00 | Project team work: Objectives & Activities Following the instruction sheet, develop: Document objectives & activities in Miradi Review with project rep during or outside class. | Instruction sheet for objectives & activities Criteria cards Computer with Miradi software (1 per group) Background documents on project |

### Required Readings:

- Background documents on project site, focusing on any strategies, objectives, goals, activities and how they all link together.

### Required Tools:

- Miradi Software – Students will use this software systematically throughout the course to document, organize, and present their project plans.