## Slide 1: Pre-planning
Planning to plan (and adapt)
Implementation starts Here!
Notes: *Note: This presentation can be shortened to focus on the following pages: 1, 4, 6, 11, 13, 20, 26
Pre-planning, or Planning to Plan, is often overlooked and seen as a step that is optional, particularly by those that just want to “get on with it”.
However, getting this step right and spending time on it will help the process to go smoothly and help people to start thinking now about implementation.
**Short List

## Slide 2
Deciding what the Plan is all about
Pre-planning
Overview
Pre-planning
Dream & Area
Targets & Health
Problems & Causes
Situation Analysis
Notes: Pre-Planning creates a work plan for the HCP process.
It also build expectations of implementation by talking about ‘what next’ as part of the planning process.
In Healthy Country Planning this Step is an important part of making sure there is Free Prior Informed Consent as it takes participants through all the steps and helps then to decide which steps they want to do and how thewy should be done.

## Slide 3
Deciding if we are we ready to proceed
Key elements for pre-planning
Think about capacity
What we produce
Deciding what the Plan is all about
Pre-planning
Overview slide

## Slide 4
Why do this step?
  create a rough work plan and approach to make sure the project gets done
  look at capacity and community needs
  be really clear with yourself and others why you want to do the plan
  identify key participants in planning and implementation
Making a plan can use a lot of time and money, so it is important to really think about how you will do it
Deciding what the Plan is all about
Pre-planning
Work out how you want to do the plan
Notes: Pre-Planning creates a work plan for the HCP process.
It also build expectations of implementation by talking about ‘what next’ as part of the planning process.
In Healthy Country Planning this Step is an important part of making sure there is Free Prior Informed Consent as it takes participants through all the steps and helps then to decide which steps they want to do and how thewy should be done.

## Slide 5
Support people to own the plan so they can drive it though the adaptive management cycle
Governance – i.e. steering committee, working group
Plan for producing interim and final products so the community understands them
Deciding what the Plan is all about
Pre-planning
Participatory planning
Notes: HCP has a strong focus on a participatory approach to making and actioning plans
That participation starts when the process of making the plan is being designed.
We think about it in terms of ‘Nothing about us without us’.
**Short List

## Slide 6
Considering previous planning exercises in the region, what is the value added?
What are the products and outcomes expected of this Healthy Country process?
Who is interested in following-through and using the Healthy Country plan?
Deciding what the Plan is all about
Pre-planning
Do we start now?
Do the community know what they want from their Healthy Country process?
Until local project leaders can articulate what they want, it is better not to proceed.
Explain what a Healthy Country process can and cannot do, and ask probing questions again.
If NO
Notes: An important part of the Pre-planning is deciding if a group / team is actually ready to develop a plan, because they might not be
Work through these questions with the group and decide if it ok to proceed or if you need to do some other work first.
There are three sets of questions to work through – the first asks if people know what they want from the process.

## Slide 7
Is there a project leader with sufficient time and the necessary skills?
Is there a Healthy Country coach to support the process as needed?
Does the team have an organization to help them?
Are minimum funds available to complete the Healthy Country process with expected products, within the expected timeframe?
Are roles & responsibilities clear?
Deciding what the Plan is all about
Pre-planning
Do we start now?
Are the minimum capacities in place to engage in a HCP project?
Until basic capacities are in place, it is better not to proceed. Determine next steps with project leaders to establish adequate conditions before starting the planning process.
If NO
Notes: These questions ask if there is enough capacity to begin the process
Capacity can be things like people, funds, skills and leadership

## Slide 8
Will funding be available to start addressing priorities?
Is there a project leader who can coordinate implementation of priorities?
Will minimum resources be available to measure strategy effectiveness?
Deciding what the Plan is all about
Pre-planning
Do we start now?
Are the conditions appropriate for implementing the plan after the planning phase is completed?
Determine how key conditions will be established for successful implementation once the planning phase is completed. If it is likely that key conditions will not be in place by the expected time, it might be better to postpone the planning phase until the scenario for implementation is clearer
If NO
Notes: This questions asks if you can actually put the pl[an into practice once you have completed the planning part
It is important to remember that the process we are talking about is not just about making a plan, but actually putting it into practice
So we need to be confident that we can proceed, or have a good chance of proceeding, once the planning is finished.

## Slide 9
Use culturally appropriate techniques
  Pre-plan meeting to build relationships & awareness
  Use 2 or more facilitators – male / female
  Use approaches to hear from all participants
  Plan to take digital photos of paper products for a record – but ask permission for all photos
  Allow time for review and feedback between meetings
Work with a smaller team on complicated steps
Don’t make first workshop your first meeting with community
Deciding what the Plan is all about
Pre-planning
Work out how you want to do the plan
Notes: When doing HCP it is important to be respectful of the culture you are working with.
Explore the idea of using interpreters, not just of the words but also the concepts
It is also important to understand the cultural conditions and behave in an appropriate way
Sometimes you will need a guide to help you with this – someone who is familiar with the community
It is good to introduce yourself to the community before you start to work – get to know people a bit first

## Slide 10
Deciding if we are we ready to proceed
Key elements for pre-planning
Think about capacity
What we produce
Deciding what the Plan is all about
Pre-planning
Overview slide

## Slide 11
Purpose: Why are we doing the plan?
Roles: Who should be involved in the plan
  Team, Sponsor, Coordinator, Facilitators, Partners
Process: How will we ‘do’ the work?
  Level of engagement, training
Timeline: What tasks done by when?
Products: What comes out the end?
Capacity: can we do this ourselves?
Deciding what the Plan is all about
Pre-planning
Work out how you want to do the plan
Notes: The things we need to talk about in the Pre-planning step are here – talk about each of these.
There are guiding questions that you can work through but if you don’t have them at least talk about expectations under each of these headings
**Short List

## Slide 12
Need a clear understanding of everyone’s reasons and goals for being in the plan
Examples of different purposes
  Project team developing biodiversity conservation strategies and measures for a single property
  Group of partners come together to develop a shared plan for a region (eg Gondwana Link)
  A community plan that can help work with other people to manage traditional lands (Indigenous Protected Area Management Plan)
  Project plan to protect important cultural sites (eg Guatemala)
Deciding what the Plan is all about
Pre-planning
Clarity of Purpose: Why are we doing the plan?
Notes: The first thing to discuss is the purpose for making the plan
There is not a ‘right’ purpose – the purpose can be decided by the group
But it is important that there is an agreed purpose.

## Slide 13
Project Team
Sponsor
Coordinator
Facilitators
Partners
Check list
Deciding what the Plan is all about
Pre-planning
Roles: Who should be involved in the plan
Notes: Once you have decided on the purpose (and that might take a while) then we talk about the different roles needed in making the HCP happen
There are more details that you can go into for each role, but if you are pressed for time you can just use these headings to have the discussion about the types of people that will make the process happen.
From here, we will talk about each of the roles in turn.
**Short List

## Slide 14
Good if you can have these in your team
  Someone who will lead the planning
  Someone who will put the plan into action
  Community leadership
  People who know the community and environment
  People good at thinking about problems / answers
  Others (e.g. partners) critical to implementation of strategies and/or measures
  Someone comfortable with computer software (desirable)
Deciding what the Plan is all about
Pre-planning
Project Team
Notes: The Project Team are the people who will make it all happen.
The list here is of the types of skills you need in your team.
That does not mean you need a team of 7 people, just that these skills should be in your team.
Also, some people might participate for some of the time and others for different steps – it might not be the same people all the way through.

## Slide 15
Sponsor gives authority to the plan
Can be person or group (e.g. elders)
They set overall purpose & any special goals
Agree on program budget, might pay or provide funding
Validate the overall process and the Project Team
Deciding what the Plan is all about
Pre-planning
Sponsor
Notes: The role of a sponsor is really important but not well understood.
The sponsor gives legitimacy to the plan – says it is ok
In a community these might be the elders, or the board

## Slide 16
Schedule and manage logistics for meetings and workshops, in consultation with the sponsor and the facilitator
Secure facilities, accommodation & meals
Maintain list & email addresses of participants
Send out announcements, reports & info
Assemble materials
Coordinate with host sites on field trip arrangements
Deciding what the Plan is all about
Pre-planning
Coordinator
Notes: If you are working with a community there is usually a coordinator who can help make things happen at the community end (or that may be you).
The coordinator will pull it all together – the process will fail without a coordinator.

## Slide 17
Co-Facilitators Recommended – “Buddy System”
Together they will usually have...
Experience in developing and implementing strategies
Good understanding of the tools you are using
Can use / learn planning software
Good listening, thinking & questioning skills
Happy to work where answers are not clear
Experience working with a variety of area plans & partners in order to adapt workshops and approach as needed
Good facilitation skills
Deciding what the Plan is all about
Pre-planning
Facilitators
Notes: Facilitators are really important to have.
It is not the role of the coordinator to put the information into the plan, but to help communities make decisions and fill in their own plan
The choice of a facilitator is really important – you don’t want a facilitator who thinks they have all the answers

## Slide 18
When do I involve partners?
Must perceive some benefit to their involvement
Need clarity of the objective/outcome
  NOTE. If partners desire different outcomes, need a clear understanding of their objectives and a process for arriving at collaborative outcomes
Not usually a “first date” with partners
  Unless the purpose and design of the agenda is well thought-through and vetted with partners and they understand the process and outcomes
Deciding what the Plan is all about
Pre-planning
Partners
Notes: Nearly every plan will need to have partners involved to implement them.
It is a big decision knowing when to involve partners.
It should be the community decision, and should be made without partners being involved in the decisions making
Partners can sometimes take the process away for the community

## Slide 19
Process: How will we ‘do’ the work?
  Level of engagement, training
  Will is just be consultation – asking people
  Or will we train people in planning
  Will there be community meetings
  Will there just be smaller meeting
  What language will we use
  Will we use written materials
Deciding what the Plan is all about
Pre-planning
Process: How will we ‘do’ the work?
Notes: Once we know who will be involved we then need to talk about the technical aspects of doing the HCP
These are the things that will really have a big impact on how long the process will take and how much it will cost
If there are a lot of community meetings then they take time and resources to bring together
But without them then it may not be possible to have good community ownership of the plan
All these elements impact on time and cost and should be considered carefully

## Slide 20
Deciding what the Plan is all about
Pre-planning
Products: What comes out the end?
Notes: We also should talk about the sorts of ‘outputs’ you are going to have at the end of the process.
It is important to do this at the start because, for example, if you want to tell a video story of your plan you will need to have captured video along the way
It will also help you to know what images you will need to capture along the way

## Slide 21
Deciding if we are we ready to proceed
Key elements for pre-planning
Think about capacity
What we produce
Deciding what the Plan is all about
Pre-planning
Overview slide

## Slide 22
Capacity: can we do this ourselves?
    Funding for help
    Remote help for process
Deciding what the Plan is all about
Pre-planning
Capacity: can we do this ourselves?
Notes: Like we did with the three questions at the start, once we have talked about all of this we should then make sure we have the capacity to do the planning
This is an example of a simple table that is sometimes used to do a capacity assessment. This one comes from the ‘old’ CAP excel workbook and works very well
If you identify some critical capacity gaps then you can set up strategies to fix them up.
**Short List

## Slide 23
Establish clear goals for the process
Respect participants time
Use enough facilitators and co-facilitators
Allow time for review and feedback
Discuss location – on-country / town
Work with a sub-group of the community on complicated steps
Preparation is the Key
Deciding what the Plan is all about
Pre-planning
Key things to consider
Notes: This is a good summary of the things to consider in pre-planning

## Slide 24
Deciding if we are we ready to proceed
Key elements for pre-planning
Think about capacity
What we produce
Deciding what the Plan is all about
Pre-planning
Overview slide

## Slide 25
Deciding what the Plan is all about
Pre-planning
Timeline: What tasks done by when?
Notes: This is an example diagram of a timeline for a HCP process involving meetings with a working group and larger community meetings.
It shows how the timeline is expected to work, and can be a good way to talk to everyone about when they need to be ready, and when they can participate

## Slide 26
Step | Who | When | Cost | Preparation
Stage of HCP | Specific people to be involved | Approx. time to complete | Budget | What needs to be done
Preparation | Elders / PBC / rangers etc | April 2011 1 day | 2 staff for 2 days plus $2k | Prepare maps, send process guide
Mapping / background | Elders, rangers, external experts | May-July 2011 2 x 1 week field | 1 staff x 10 days, plus $50k | Logistics
Boundary / Dream/ Targets | Community | July 2011 4 days | 2 staff for 10 days plus $20k | Camp site, catering, background reports
Health / Threats + review | Staff | Aug - Sept 2011 5 days | 1 staff x 5 days | Complete Targets
Situation Analysis + review | Steering Group | Sept 2011 2 days | 1 staff x 5 days plus $5k | Complete Viability
Goals / Strategies + review | Community | October 2011 4 days | 2 staff for 10 days plus $20k | Camp site, catering, background reports
Action Planning + review | Steering Group | November 2011 4 days | 2 staff x 5 days plus $5k | Complete Strategies
Drafting | Staff | Dec-Mar 2011/12 20 days | 1 staff x 20 days plus $15k | All stages completed
Approval | Community | April 2012 2 days | 2 staff for 5 days plus $20k | All stages completed
Deciding what the Plan is all about
Pre-planning
A 12 month example
Notes: Once you have thought about all the elements you might then also put them into a table to make a workplan for the planning team
There is not a right way to do this, but it is a useful thing to show people what the jobs are and the responsibilities for those jobs.
**Short List

## Slide 27
Deciding what the Plan is all about
Pre-planning
Additional resources
Notes: There are a lot of useful resources available for people who want to do these steps.
These three documents provide some useful tools to do this step and record the results.

## Slide 28: Attribution
Product of the Conservation Coaches Network, 2019
These presentations were adopted of materials from members of the Conservation Coaches Network.
CCNet strongly recommends that this presentation is given by experts familiar with the adaptive management process presented by the Conservation Measures Partnership’s Open Standards for the Practice of Conservation / Community of Practice – Indigenous CS projects and CS projects on Indigenous Land and Waters.
You are free to share this presentation and adapt it for your use. Please attribute the work to CCNet. If you significantly alter, transform, or build upon this work, it may be appropriate to remove the HCP logo.