## Slide 1: Closing the circle and Reviewing the plan

## Slide 2
Deciding what the plan is about
Making the plan
Doing and monitoring the work
Deciding if the plan is working
Telling ourselves and others
Getting data
Looking at results
Adapting the plan

## Slide 3
Deciding if the plan is working
Closing the Circle
Overview Presentation
What is a MERI plan trying to do?
Linking MERI to the result chain
Progress Reporting
A culture of review

## Slide 4
Deciding if the plan is working
Closing the Circle
Key steps
Ensure data gathered answers the key questions
  Annual implementation, periodic effectiveness and status
Gather / store / analyse data
Interpret and communicate results
Adapt the plan / strategy
Create a culture of review
  Self assessment
  Peer review

## Slide 5
A Management Plan sets out what we think is going to happen – which things we will do, what impact we think we will have
A Monitoring, Evaluation, Reporting and Improvement Plan sets out how we are going to check, and what we will do with the results

## Slide 6
Deciding if the plan is working
Closing the Circle
What is in a MERI?
How will we collect and use information?
How will we collect and use information?
How will we collect and use information?

## Slide 7
Deciding if the plan is working
Closing the Circle
The Language of MERI - Illustrated
Impacts
Is the Target healthy?
What needs to change?
Outcomes
Is the threat reducing?
What needs to change?
Inputs and Outputs
Have we done the work?
Do we need to do more?
Targets
Threats
Strategies
Actions
Wetland health
Build cattle-proof fencing
Intensive management around wetlands
Wetlands
By 2020 cattle are managed so they do not damage wetlands
How much fencing did we build? Where?
How many cattle in wetlands?
How much did it cost?
Cattle damage at wetlands
PLAN
INDICATORS
MERI
This diagram shows how the ideas on the previous page fit together

## Slide 8
Deciding if the plan is working
Closing the Circle
The more we measure, the more confident we can be
Targets
(Impacts)
Threat
(Outcomes)
Reduction
Strategies
Actions
(Outputs)
Relative cost of measuring change
Confidence in Impact
Time needed to see change

## Slide 9
Deciding if the plan is working
Closing the Circle
What results are we looking for?
Ideal
Little effort or more
High Outcome and Impact
Not Ideal
High effort
Low Outcome and Impact
Not Understanding
High effort
Low Outcome and High Impact
Could also be High outcome and Low impact
Impacts
Is the Target healthy?
What needs to change?
Outcomes
Is the threat reducing?
What needs to change?
Inputs and Outputs
Have we done the work?
Do we need to do more?
HIGH
LOW

## Slide 10
 | Data / Information | Analyse | Adapt
Impact |  |  | 
Outcomes |  |  | 
Outputs |  |  | 
Deciding if the plan is working
Closing the Circle
Nine elements are needed

## Slide 11
Deciding if the plan is working
Closing the Circle
Process needs
REPORTING TOOLS
DATA MANAGEMENT TOOLS
Field work implements work plan
Monitoring data captured
Monitoring data stored/ retrieved
Clear questions from plan
Report and adaptation
Actions from plan
Indicators from Plan
DATA CAPTURE TOOLS
DATA ANALYSIS TOOLS
Data prepared and analysed

## Slide 12
Deciding if the plan is working
Closing the Circle
Overview Presentation
What is a MERI plan trying to do?
Linking MERI to road maps
Progress Reporting
A culture of review

## Slide 13
Key questions
  Are key steps in our plan missing or needing more work?
    Self-assessment / peer review
  Are we using our plan?
    Progress reports on actions
  Is our plan logical? Does it make sense?
    Check our results chains and test our thinking
  What are our results telling us?
    Analyse our data, interpret, and adapt
  What have we learned so far and who should we tell?
    Share our learnings
Deciding if the plan is working
Closing the Circle
Where are we at?

## Slide 14
What question are we asking?
Every year - are we using the plan?
Every 1-3 years - Are the strategies working?
Every 5-10 years - Are our targets improving?
Gather Indicator measurements
# proposals written
# grants received
# households contacted
# Units switched
volume of wood consumed
Changes in forest cover
- forest health indicators
Reflect and Interpret data
Are we progressing all the actions as planned? If not, why not?
Are we progressing fast enough?
What helped us?
What stopped us?
Is forest health improving?
Adapt
Do we need new actions?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Input / Output
Outcome
Impact
Outreach efforts & install alternative energy devices
Switch to efficient heating and cooking devices
Reduce burning of fuelwood
Reduce logging
Forests

## Slide 15
Deciding if the plan is working
Closing the Circle
Progress ratings
Done Successfully accomplished | 
Working well Ongoing, generally on track | 
Little problem that needs fixing: Ongoing, but has minor issues that need attention | 
Big problem that needs fixing: Ongoing, but has major issues that need attention | 
Abandoned No longer important | 
Yet to do Activity is not yet started | NA

## Slide 16
Mid-term reviews
Deciding if the plan is working
Closing the circle

## Slide 17
What question are we asking?
Every year - are we using the plan?
Every 1-3 years - Are the strategies working?
Every 5-10 years - Are our targets improving?
Gather Indicator measurements
# proposals written
# grants received
# households contacted
# Units switched
volume of wood consumed
Changes in forest cover
- forest health indicators
Reflect and Interpret data
Are we progressing all the actions as planned? If not, why not?
Is our data enough
Are we progressing fast enough?
What helped us?
What stopped us?
Is forest health improving?
Adapt
Do we need new actions?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Input / Output
Outcome
Impact
Outreach efforts & install alternative energy devices
Switch to efficient heating and cooking devices
Reduce burning of fuelwood
Reduce logging
Forests

## Slide 18
Deciding if the plan is working
Closing the Circle
Revising the Threat table
Analysis of fox control measures tells us this risk can now be changed to Medium
But we weren’t monitoring or controlling weeds here and now the threat has increased because it’s getting more recreation use

## Slide 19
What question are we asking?
Every year - are we using the plan?
Every 1-3 years - Are the strategies working?
Every 5-10 years - Are our targets improving?
Gather Indicator measurements
# proposals written
# grants received
# households contacted
# Units switched
volume of wood consumed
Changes in forest cover
- forest health indicators
Reflect and Interpret data
Are we progressing all the actions as planned? If not, why not?
Is our data enough
Are we progressing fast enough?
What helped us?
What stopped us?
Is forest health improving?
Adapt
Do we need new actions?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Do we need new strategy/action?
Do we need more resourcing?
Input / Output
Outcome
Impact
Outreach efforts & install alternative energy devices
Switch to efficient heating and cooking devices
Reduce burning of fuelwood
Reduce logging
Forests

## Slide 20
Deciding if the plan is working
Closing the Circle
Updating the Health Table
 | Conservation Targets | Landscape Context | Condition | Size | Viability Rank
 | Current Rating |  |  |  | 
1 | Eucalypt woodlands | Fair | Fair | Good | Fair
2 | Sandplain shrublands | Good | Fair | - | Good
3 | Granite exposures and breakaways | Good | Good | Good | Good
4 | Hills (Banded Ironstone Formations) | Fair | Fair | - | Fair
5 | Lake Cronin | Good | - | Fair | Good
6 | Saltlakes | Good | Good | - | Good
7 | Dingo | - | - | Fair | Fair
8 | Chuditch | - | Fair | Good | Good
9 | Malleefowl | - | Good | Good | Good
10 | Carnaby's Cockatoo | - | Fair | Fair | Fair
 | Project Biodiversity Health Rank |  |  |  | Good
 | Conservation Targets | Landscape Context | Condition | Size | Viability Rank
 | Current Rating |  |  |  | 
1 | Eucalypt woodlands | Fair | Fair | Good | Fair
2 | Sandplain shrublands | Good | Fair | - | Good
3 | Granite exposures and breakaways | Good | Good | Good | Good
4 | Hills (Banded Ironstone Formations) | Fair | Fair | - | Fair
5 | Lake Cronin | Good | - | Fair | Good
6 | Saltlakes | Good | Good | - | Good
7 | Dingo | - | - | Fair | Fair
8 | Chuditch | - | Fair | Fair | Fair
9 | Malleefowl | - | Good | Fair | Fair
10 | Carnaby's Cockatoo | - | Fair | Fair | Fair
 | Project Biodiversity Health Rank |  |  |  | Good
Target health at start of project
Updated after 8 years monitoring

## Slide 21
Deciding if the plan is working
Closing the Circle
Overview Presentation
What is a MERI plan trying to do?
Linking MERI to road maps
Progress Reporting
A culture of review

## Slide 22
Deciding if the plan is working
Closing the Circle
Progress reporting

## Slide 23
Deciding if the plan is working
Closing the Circle
Progress reporting

## Slide 24
Deciding if the plan is working
Closing the Circle
Progress reporting

## Slide 25
Deciding if the plan is working
Closing the Circle
Overview Presentation
What is a MERI plan trying to do?
Linking MERI to road maps
Progress Reporting
A culture of review

## Slide 26
We want review to become a good habit
To do that it needs to be a regular part of business
Needs a commitment to support, review and act on outcomes
Internally driven for benefit (carrot) not compliance (stick)
Deciding if the plan is working
Closing the Circle
Culture of review

## Slide 27: Uunguu Monitoring and Evaluation Committee

## Slide 28
Deciding if the plan is working
Closing the Circle
Additional Resources

## Slide 29
Keeping your plan ‘alive’ is important for long-term success and it requires regular review and discussion, as well as regular updating.
You might need help from other people to do this, and resources to do it.
We are going to ‘practice’ plan review by looking back at the Pre-Plan work you did and adapting that ‘plan’ based on what you now know about the process.
In your team discuss and record what changes (if any) you need to make to the Pre-plan, and then revise that Pre-plan to make a new one.
Deciding if the plan is working
Closing the Circle
Exercise